## Sheet1
Ashoka East Africa
SuiteVolunteers: Aprille Ibarra; Lorrenzo Santos; Carol Tragura
Date (GMT) | Agenda | Hours Spent | Other Information
2014-05-15 | Introduction/Kick-Off Meeting with Grantee | 1
Ashoka East Africa has its main office in Washington DC that already uses NetSuite. They also want to be able to use NetSuite just like the said office. They want to get familiarized with NetSuite features (ERP) that they may use for their processes. They are expecting to have some sort of a training
2014-05-21 | Data Gathering | 1
2014-05-26 | Sign Off Project Brief | 0
2014-05-28 | Training Sessio# 1: Procure to Pay | 2
2014-06-04 | Training Session#2: Order to Cash | 2
2014-06-11 | Training Session# 3: Journal Entries; Transfer Funds; Bank Statement Reconciliation; Reports and Searches Overview | 2
2014-06-18 | Training Session#4: Reports and Searches | 2 | Ashoka was provided training on how to create saved searches and reports. They will be the one to cusotmize the searches and reports based on how they need it
2014-06-30 | Final Session: Q&A based on activities provided to grantee (Creation of Reports based on their requirement). Support provided to them | 2
2014-06-30 | Sign off Project Completion | 0